## Tracker
Workstream | Owner | Status | Due | Evidence | Source
Supplier import | Maya Chen | Complete | 2026-11-06 | 24 of 24 records imported and validated | 01.eml (Maya Chen); import-checks.csv
Billing QA | Eli Brooks | Complete | 2026-11-04 | 12 of 12 checks passed; release remains Nov 4 | 02.eml (Eli Brooks); billing-qa.csv
Launch checklist | Nora Patel | At risk | 2026-11-06 | Copy approved; security review Nov 3 10:00 UTC, no approval yet | 03.eml (Nora Patel); 04.eml (Maya Chen); calendar.ics

## Summary
Lark weekly status - week of Nov 2, 2026
Status | Workstreams
Complete | 2
In progress | 0
At risk | 1
Total | 3
Tracker rows | 3 | ties
Check | Passed | Total | Pass rate | Source
Supplier records | 24 | 24 | 100% | import-checks.csv
Billing QA | 12 | 12 | 100% | billing-qa.csv
All checks | 36 | 36 | 100%
Evidence text matches counts? | yes